## Plan_K_N-S_09-15-20_XD2
Operations start time | [6 empty] | 2020-08-31 16:00 |  |  | Update time: | 9/14/2020 09:06:00 AM
[6 empty] | Distance | Time | Cumulative
Langseth |  |  |  | # | #teth | (km) | (Days) | (Hours) | Days | Date
Depart | SP wet | Dep | Rec | SP dry | 1h turn |  |  |  |  | 2020-08-31 16:00
Transit Ketchikan to Rosette | [5 empty] | 1650 | 3.92 | 94.0791 | 3.92 | 2020-09-04 14:05
(gun maintenance in turns) | [10 empty] | locks
Rosette test | 0 |  |  | 61 | 1 | 1 | 0.14587 | 3.5008 | 4.0658 | 2020-09-04 17:35
Change to Adak time (-1hr) | 61 | 0 | 0 | 0 | 0 | 0 | -0.041667 | -1 | 4.0242 | 2020-09-04 16:35
Transit Rosette to S1_E | 0 | 0 | 0 | 61 | 0 | 1120 | 2.6524 | 63.6581 | 6.6766 | 2020-09-07 08:14
Deploy S1 e-w (1-2) transit to S1(3) | 2 | 2 | 0 | 59 | 0 | 30 | 0.098825 | 2.3718 | 6.7754 | 2020-09-07 09:35 | 9/7/2020 9:35:00 AM |  | 2020-09-25
Deploy S1 e-w (3-8) | 8 | 6 | 0 | 53 | 0 | 63 | 0.23253 | 5.5808 | 7.0079 | 2020-09-07 14:18 | 9/7/2020 2:18:00 PM |  | 2020-08-10
Transit to D1(8) | 8 | 0 | 0 | 53 | 0 | 75 | 0.17762 | 4.2628 | 7.1856 | 2020-09-07 19:00 | 9/7/2020 7:00:00 PM |  | 46
Deploy D1(8,9) S1 (9,10,11) transit to S1(12) | 13 | 5 | 0 | 48 | 0 | 50 | 0.18786 | 4.5085 | 7.3734 | 2020-09-08 00:10 | 9/8/2020 12:10:00 AM
Deploy S1 (12-18) | 20 | 7 | 0 | 41 | 0 | 65 | 0.25116 | 6.0278 | 7.6246 | 2020-09-08 05:39 | 9/8/2020 05:39:00 AM
Transit to D2(6) | 20 | 0 | 0 | 41 | 0 | 50 | 0.11841 | 2.8419 | 7.743 | 2020-09-08 08:30 |  |  | 2020-10-14
Deploy D2(6) S1(19,20,21,22) | 25 | 5 | 0 | 36 | 0 | 40 | 0.16417 | 3.9402 | 7.9072 | 2020-09-08 13:28 | 9/8/2020 01:28:00 PM |  | 2020-08-10
Transit to S1(23) | 25 | 0 | 0 | 36 | 0 | 25 | 0.059206 | 1.4209 | 7.9664 | 2020-09-08 14:53
Deploy S1(23,24,25,26,27) transit to S1(28) | 30 | 5 | 0 | 31 | 0 | 125 | 0.36547 | 8.7714 | 8.3318 | 2020-09-08 23:55 | 9/8/2020 11:55:00 PM |  | 65
Deploy S1(28,29,30) | 33 | 3 | 0 | 28 | 0 | 30 | 0.11271 | 2.7051 | 8.4445 | 2020-09-09 02:31 | 9/9/2020 02:31:00 AM
Deploy Guns, turn around, come online | 33 | 0 | 0 | 28 | 0 |  | 0.16667 | 4 | 8.6112 | 2020-09-09 10:31 | 9/9/2020 10:31:00 AM
Shoot Line S1 OBS W to E | 33 | 0 | 0 | 28 | 0 | 550 | 2.7914 | 66.9947 | 11.4027 | 2020-09-12 02:33 | 9/12/2020 2:33:00 AM
Recover guns | 33 | 0 | 0 | 28 | 0 |  | 0.041667 | 1 | 11.4443 | 2020-09-12 04:23 | 9/12/2020 4:23:00 AM
Recover S1 e-w (1-2) transit to S1(3) | 31 | 0 | 2 | 30 | 0 | 30 | 0.13259 | 3.1821 | 11.5769 | 2020-09-12 09:15 | 9/12/2020 9:15:00 AM
Recover S1 (3-8) | 25 | 0 | 6 | 36 | 0 | 63 | 0.33383 | 8.0118 | 11.9107 | 2020-09-12 16:35 | 9/12/2020 4:35:00 PM
Transit to S1 8 to 9 | 25 | 0 | 0 | 36 | 0 | 70 | 0.16578 | 3.9786 | 12.0765 | 2020-09-12 21:18 | 9/12/2020 9:18:00 PM
Recover S1 (9,10) | 23 | 0 | 2 | 38 | 0 | 35 | 0.14443 | 3.4663 | 12.2209 | 2020-09-13 00:24 | 9/13/2020 12:24:00 AM
Recover S1 (13 to 18) | 17 | 0 | 6 | 44 | 0 | 65 | 0.33856 | 8.1255 | 12.5595 | 2020-09-13 08:04 | 9/13/2020 08:04:00 AM
Transit to D2(6) | 17 | 0 | 0 | 44 | 0 | 50 | 0.11841 | 2.8419 | 12.6779 | 2020-09-13 10:55
Recover D2(6), S1(19,20,21,22) | 12 | 0 | 5 | 49 | 0 | 70 | 0.31963 | 7.6712 | 12.9976 | 2020-09-13 17:29 | 9/13/2020 05:29:00 PM
Transit to S1(22) to S1(23) | 12 | 0 | 0 | 49 | 0 | 25 | 0.059206 | 1.4209 | 13.0568 | 2020-09-13 19:22 | 9/13/2020 07:22:00 PM
Recover S1(23,24,25,26,27) transit to S1(28) | 7 | 0 | 5 | 54 | 0 | 123 | 0.44515 | 10.6835 | 13.5019 | 2020-09-14 05:23 | 9/14/2020 05:23:00 AM
Recover S1 (28,29,30) | 4 | 0 | 3 | 57 | 0 | 70 | 0.25809 | 6.1941 | 13.76 | 2020-09-14 09:06 | 9/14/2020 09:06:00 AM
Transit S1_W to D1(1) | 4 | 0 | 0 | 57 | 0 | 300 | 0.71047 | 17.0513 | 14.4705 | 2020-09-15 02:09
Deploy D1 n-s (1-4) transit to D1(5) | 8 | 4 | 0 | 53 | 0 | 58 | 0.19291 | 4.6299 | 14.6634 | 2020-09-15 06:50 | 9/15/2020 06:50:00 AM
Deploy D1 n-s (5-7) transit to D1(8) | 11 | 3 | 0 | 50 | 0 | 38 | 0.13166 | 3.1598 | 14.795 | 2020-09-15 10:48 | 9/15/2020 10:48:00 AM
Transit D1_8 to D1_11 | 11 | 0 | 0 | 50 | 0 | 120 | 0.28419 | 6.8205 | 15.0792 | 2020-09-15 17:37
Deploy D1 n-s (11,12,13) transit to D1(14) | 14 | 3 | 0 | 47 | 0 | 36 | 0.12692 | 3.0462 | 15.2061 | 2020-09-15 20:40
Deploy D1 n-s (14,15,16) transit to D1(17) | 17 | 3 | 0 | 44 | 0 | 62 | 0.1885 | 4.5239 | 15.3946 | 2020-09-16 01:11
Deploy D1 n-s (17,18,19) | 20 | 3 | 0 | 41 | 0 | 30 | 0.11271 | 2.7051 | 15.5074 | 2020-09-16 03:54
Deploy D1 n-s (21,23,25) | 20 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 15.5074 | 2020-09-16 03:54
Deploy Guns/ turn around | 20 | 0 | 0 | 41 | 0 |  | 0.0625 | 1.5 | 15.5699 | 2020-09-16 05:24
Shoot D1 run-in to D19 | 20 | 0 | 0 | 41 | 0 | 340 | 1.7415 | 41.7967 | 17.3114 | 2020-09-16 04:45 | 9/16/2020 4:45:00 AM
Shoot D1 OBS D1(19) to D1(16) + compressor maint | 20 | 0 | 0 | 41 | 0 | 45 | 0.22498 | 5.3996 | 17.5364 | 2020-09-16 11:35 | 9/16/2020 11:35:00 AM
Shoot D1 OBS D1(16) to D1(11) | 20 | 0 | 0 | 41 | 0 | 65 | 0.32497 | 7.7994 | 17.8613 | 2020-09-16 19:23
Shoot D1 OBS D1(11) to S1(11) | 20 | 0 | 0 | 41 | 0 | 110 | 0.54996 | 13.1989 | 18.4113 | 2020-09-17 07:15 | 9/17/2020 7:15:00 AM
Shoot D1 OBS S1(11) to D1(5) | 20 | 0 | 0 | 41 | 0 | 60 | 0.29998 | 7.1994 | 18.1613 | 2020-09-17 14:05 | 9/17/2020 2:05:00 PM
Shoot D1 OBS D1(5) to D1(1) | 20 | 0 | 0 | 41 | 0 | 58 | 0.28998 | 6.9594 | 18.7013 | 2020-09-17 21:03
Recover guns | 20 | 0 | 0 | 41 | 0 |  | 0.041667 | 1 | 18.7429 | 2020-09-17 22:03
Recover D1 n-s (1-4) | 16 | 0 | 4 | 45 | 0 | 44 | 0.39529 | 9.4869 | 19.1382 | 2020-09-18 07:32
Transit to D1(4) to D1(5) | 16 | 0 | 0 | 45 | 0 | 14 | 0.033155 | 0.79573 | 19.1714 | 2020-09-18 08:26 | 9/18/2020 8:26:00 AM
Recover D1(5) | 15 | 0 | 1 | 46 | 0 | 0 | 0.075164 | 1.8039 | 19.2465 | 2020-09-18 09:35 | 9/18/2020 9:35:00 AM
Transit to D1(5) to D1(6) | 15 | 0 | 0 | 46 | 0 | 12 | 0.028419 | 0.68205 | 19.275 | 2020-09-18 10:16
Recover D1(6) | 14 | 0 | 1 | 47 | 0 | 0 | 0.075164 | 1.8039 | 19.3501 | 2020-09-18 11:35 | 9/18/2020 11:35:00 AM
Transit D1(6) to D1(7) | 14 | 0 | 0 | 47 | 0 | 12 | 0.028419 | 0.68205 | 19.3785 | 2020-09-18 12:16
Recover D1(7) | 13 | 0 | 1 | 48 | 0 | 0 | 0.075164 | 1.8039 | 19.4537 | 2020-09-18 13:20 | 9/18/2020 1:20:00 PM
Transit D1(7) to D1(8) | 13 | 0 | 0 | 48 | 0 | 12 | 0.028419 | 0.68205 | 19.4821 | 2020-09-18 14:01
Recover D1(8) | 12 | 0 | 1 | 49 | 0 | 0 | 0.038313 | 0.91951 | 19.5204 | 2020-09-18 14:56
Transit D1(8) to D1(9) | 12 | 0 | 0 | 49 | 0 | 12 | 0.028419 | 0.68205 | 19.5489 | 2020-09-18 15:37
Recover D1(9) | 11 | 0 | 1 | 50 | 0 | 0 | 0.038313 | 0.91951 | 19.5872 | 2020-09-18 16:30 | 9/18/2020 4:30:00 PM
Transit D1(9) to S1(11) | 11 | 0 | 0 | 50 | 0 | 11 | 0.026051 | 0.62521 | 19.6132 | 2020-09-18 17:08
Recover S1(11) | 10 | 0 | 1 | 51 | 0 | 0 | 0.016882 | 0.40517 | 19.6301 | 2020-09-18 17:40 | 9/18/2020 5:40:00 PM
Transit S1(11) to S1(12) | 10 | 0 | 0 | 51 | 0 | 11 | 0.026051 | 0.62521 | 19.6562 | 2020-09-18 18:18
Recover S1(12) | 9 | 0 | 1 | 52 | 0 | 0 | 0.016882 | 0.40517 | 19.673 | 2020-09-18 18:35 | 9/18/2020 6:35:00 PM
Transit S1(12) to D1(19) | 9 | 0 | 0 | 52 | 0 | 180 | 0.42628 | 10.2308 | 20.0993 | 2020-09-19 04:49
Recover D1(19) | 8 | 0 | 1 | 53 | 0 | 0 | 0.08541 | 2.0498 | 20.1847 | 2020-09-19 06:50 | 9/19/2020 6:50:00 AM | No response
Transit D1(19) to D1(18) | 8 | 0 | 0 | 53 | 0 | 15 | 0.035523 | 0.85256 | 20.2203 | 2020-09-19 07:41
Recover D1(18) | 7 | 0 | 1 | 54 | 0 | 0 | 0.08541 | 2.0498 | 20.3057 | 2020-09-19 09:30 | 9/19/2020 9:30:00 AM
Transit D1(18) to D1(17) | 7 | 0 | 0 | 54 | 0 | 15 | 0.035523 | 0.85256 | 20.3412 | 2020-09-19 10:21
Recover D1(17) | 6 | 0 | 1 | 55 | 0 | 0 | 0.08541 | 2.0498 | 20.4266 | 2020-09-19 12:01 | 9/19/2020 12:00:00 PM
Transit D1(17) to D1(16) | 6 | 0 | 0 | 55 | 0 | 14 | 0.033155 | 0.79573 | 20.4598 | 2020-09-19 12:49
Recover D1(16) | 5 | 0 | 1 | 56 | 0 | 0 | 0.098429 | 2.3623 | 20.5582 | 2020-09-19 14:25 | 9/19/2020 2:25:00 PM
Transit D1(16) to D1(15) | 5 | 0 | 0 | 56 | 0 | 14 | 0.033155 | 0.79573 | 20.5913 | 2020-09-19 15:13
Recover D1(15) | 4 | 0 | 1 | 57 | 0 | 0 | 0.094799 | 2.2752 | 20.6861 | 2020-09-19 17:12 | 2020-09-19 17:12
Transit D1(15) to D1(14) | 4 | 0 | 0 | 57 | 0 | 14 | 0.033155 | 0.79573 | 20.7193 | 2020-09-19 18:00
Recover D1(14) | 3 | 0 | 1 | 58 | 0 | 0 | 0.071725 | 1.7214 | 20.791 | 2020-09-19 19:12 | 2020-09-19 19:12
Transit D1(14) to D1(13) | 3 | 0 | 0 | 58 | 0 | 12 | 0.028419 | 0.68205 | 20.8194 | 2020-09-19 19:53
Recover D1(13) | 2 | 0 | 1 | 59 | 0 | 0 | 0.042153 | 1.0117 | 20.8616 | 2020-09-19 20:34 | 2020-09-19 20:34
Transit D1(13) to D1(12) | 2 | 0 | 0 | 59 | 0 | 12 | 0.028419 | 0.68205 | 20.89 | 2020-09-19 21:15
Recover D1(12) | 1 | 0 | 1 | 60 | 0 | 0 | 0.028591 | 0.68619 | 20.9186 | 2020-09-19 21:47 | 2020-09-19 21:47
Transit D1(12) to D1(11) | 1 | 0 | 0 | 60 | 0 | 12 | 0.028419 | 0.68205 | 20.947 | 2020-09-19 22:28
Recover D1(11) | 0 | 0 | 1 | 61 | 0 | 0 | 0.027334 | 0.65602 | 20.9744 | 2020-09-19 22:58 | 2020-09-19 22:58
Transit to D1_S to Dutch | 0 | 0 |  | 61 |  | 675 | 1.5496 | 37.1909 | 22.524 | 2020-09-21 12:00 | To Dutch from D1_S (675)
Offload OBSIC personnel | 0 | 0 |  | 61 |  | 10 | 0.25 | 6 | 22.774 | 2020-09-21 16:00
Transit Dutch to Amlia | 0 | 0 |  | 61 |  | 675 | 1.5496 | 37.1909 | 24.3236 | 2020-09-23 00:30
Deploy Streamer | 0 | 0 |  | 61 |  | 0 | 1.5 | 36 | 25.8236 | 2020-09-23 16:10
Deploy Guns/ turn around | 0 | 0 |  | 61 |  | 0 | 0.083333 | 2 | 25.9069 | 2020-09-23 16:10 | ended test line and turning toward AF01
Shoot mcs AFZ1 | 0 | 0 |  | 61 | 0 | 70 | 0.34997 | 8.3993 | 26.2569 | 2020-09-24 00:34
Shoot mcs AFZ2 | 0 | 0 |  | 61 | 0 | 18 | 0.089993 | 2.1598 | 26.3469 | 2020-09-24 02:44
Shoot mcs AFZ3 | 0 | 0 |  | 61 | 0 | 70 | 0.34997 | 8.3993 | 26.6969 | 2020-09-24 11:15 | 9/24/2020 11:15:00 AM
Shoot mcs AFZ4 | 0 | 0 |  | 61 | 0 | 18 | 0.089993 | 2.1598 | 26.7869 | 2020-09-24 13:25
Shoot mcs AFZ5 | 0 | 0 |  | 61 | 0 | 70 | 0.34997 | 8.3993 | 27.1368 | 2020-09-24 21:49
Shoot mcs AFZ"6" | 0 | 0 |  | 61 | 0 | 24 | 0.11999 | 2.8798 | 27.2568 | 2020-09-25 11:45 | 9/25/2020 11:45:00 AM
Shoot D1S MCS s to n | 0 | 0 |  | 61 | 0 | 245 | 1.2249 | 29.3976 | 28.4817 | 2020-09-26 17:09
Transit to D1S(n) to D2S(n) | 0 | 0 |  | 61 | 0 | 110 | 0.54996 | 13.1989 | 29.0317 | 2020-09-27 03:00 | 9/27/2020 3:00:00 AM
Shoot D2S MCS n to s | 0 | 0 |  | 61 | 0 | 165 | 0.82493 | 19.7984 | 29.8566 | 2020-09-27 23:35 | 9/27/2020 11:35:00 PM
Shoot D2S to S1W connector | 0 | 0 |  | 61 | 2 | 270 | 1.4332 | 34.3974 | 31.2898 | 2020-09-29 09:59
Transit, shorten streamer to 6 km | 0 | 0 |  | 61 | 0 | 55 | 0.27498 | 6.5995 | 31.5648 | 2020-09-29 16:35
Shoot S1A MCS w to e | 0 | 0 |  | 61 | 2 | 42 | 0.29332 | 7.0396 | 31.8581 | 2020-09-29 21:58 | 9/29/2020 9:58:00 PM
Shoot S1B MCS w to e | 0 | 0 |  | 61 | 0 | 26 | 0.12999 | 3.1198 | 31.9881 | 2020-09-30 01:00 | 9/30/2020 1:00:00 AM
Shoot S1C MCS w to e | 0 | 0 |  | 61 | 0 | 178 | 0.88993 | 21.3583 | 32.8781 | 2020-09-30 22:25 | 9/30/2020 10:25:00 PM
Shoot S1D MCS w to e | 0 | 0 |  | 61 | 0 | 87 | 0.43497 | 10.4392 | 33.313 | 2020-10-01 08:51
Turn to D1N | 0 | 0 |  | 61 | 0 | 15 | 0.074994 | 1.7999 | 33.388 | 2020-10-01 07:50 | 10/1/2020 07:50:00 AM
Shoot D1N MCS s to n | 0 | 0 |  | 61 | 0 | 122 | 0.60995 | 14.6388 | 33.998 | 2020-10-01 22:55 | 10/1/2020 10:55:00 PM
Shoot D1N to S1w connector | 0 | 0 |  | 61 | 2 | 200 | 1.0833 | 25.9981 | 35.0812 | 2020-10-03 00:05 | 10/3/2020 12:05:00 AM
Shoot S1G e to w | 0 | 0 |  | 61 | 1 | 94 | 0.51163 | 12.2791 | 35.5928 | 2020-10-03 12:22 |  | 510
Shoot S1F e to w | 0 | 0 |  | 61 | 1 | 83 | 0.45663 | 10.9592 | 36.0495 | 2020-10-03 20:15 | 10/3/2020 8:15:00 PM
Shoot S1E e to w (including east end of S1D) | 0 | 0 |  | 61 | 1 | 52 | 0.30165 | 7.2395 | 36.3511 | 2020-10-04 02:52 | 10/4/2020 2:52:00 AM
Transit S1 to D2N | 0 | 0 |  | 61 | 0 | 140 | 0.69994 | 16.7987 | 37.0511 | 2020-10-04 19:21 | 10/4/2020 7:21:00 PM
Shoot D2N n to s | 0 | 0 |  | 61 | 1 | 115 | 0.61662 | 14.7989 | 37.6677 | 2020-10-05 08:50 | 10/5/2020 8:50:00 AM
Recover guns | 0 | 0 |  | 61 |  | 0 | 0.083333 | 2 | 37.751 | 2020-10-05 10:02 | 10/5/2020 10:02:00 AM | recovered 2 strings before eol and turn, then two after
Recover streamer | 0 | 0 |  | 61 |  | 0 | 0.5 | 12 | 38.251 | 2020-10-05 13:05 | 10/5/2020 1:05:00 PM
Transit to Dutch | [5 empty] | 700 | 1.607 | 38.5683 | 39.858 | 2020-10-07 03:39
Contingency | 0 | 0 |  | 61 |  | 0 | 10.1812 | 244.3483 |  | 2020-10-17 08:00
Locked contingency, weather | [6 empty] | 0 | 0 | 39.858 | 2020-10-07 03:39
Locked contingency, gear | [6 empty] | 0 | 0 | 39.858 | 2020-10-07 03:39
Contingency | [7 empty] | 0 | 39.858 | 2020-10-07 03:39
50.3392
1 UNOLS day at the dock | [6 empty] | 1
Total ship days needed | [5 empty] | 51.3392
Transit days | 8.1794
Science days | 43.1598 | [7 empty] | 46.5686
Nobs | 61
Units
NMiles/km |  |  |  | 0.53996
km/NMiles |  |  |  | 1.852 |  |  |  | 1 | 24
[8 empty] | 2 | 48
Factors | [7 empty] | 3 | 72
Transit speed (knts) |  |  |  | 9.8 |  |  |  | 4 | 96
Langseth transit speed (knts) |  |  |  | 9.8 |  |  |  | 5 | 120
Deploy Transit speed (knts) |  |  |  | 9.5 |  |  |  | 6 | 144
OBS Deployment, Un-tethered (hrs) |  |  |  | 0.33333 |  |  |  | 7 | 168
OBS Deployment, Tethered time (hrs) |  |  |  | 0.775
OBS, Avg. Recovery time (hrs), S1 |  |  |  | 0.73851
OBS, Avg. Recovery time (hrs), D1_N |  |  |  | 1.6144
OBS, Avg. Recovery time (hrs), D1_S |  |  |  | 1.9057 |  |  |  |  | 2.325
OBS, Avg. Recovery time (hrs), D2_N |  |  |  | 2.3506
OBS, Avg. Recovery time (hrs), D2_S |  |  |  | 2.3506
Wide-angle shooting (knts) |  |  |  | 4.5
MCS shooting (knts) |  |  |  | 4.5
hydrowire speed (m/s) |  |  |  | 0.68333
tether wire out (m/min) |  |  |  | 40
average tether out time (hrs) | 21500 | 25 |  | 0.775 | (These are mariana numbers)
averge tethering time, aleut D1 (hrs) | 7500 | 6 |  | 0.9375
averge tethering time, aleut D2 (hrs) | 7000 | 4 |  | 1.1458
average tether out time (hrs) | 14500 | 10 |  | 1.0208 | (These are aleut numbers)
Avg Depth
D1_N | 2990
D1_S | 3835
D2_N | 2950
D2_S | 2950
Average inst depth (m), S1 | 450
Average inst depth (m), D1_N | 2990
Average inst depth (m), D1_S | 3835
Average inst depth (m), D2_N | 2950
Average inst depth (m), D2_S | 2950
Avg inst Rise rate (m/s) | 0.80556
Average inst depth (m) | 4720
Average rise time (hrs), S1 | 0.40517
Average rise time (hrs), D1_N | 1.281
SIO Rise rate (m/s) | 0.75
WHOI Rise rate (m/s) | 0.91667
Average rise time (hrs), D1_1-2 | 1.7736 |  |  |  |  | D1_1-2_Z | 3762.955
Average rise time (hrs), D1_1-2 | 1.7465 |  |  |  |  | D1_1-4_Z | 3673.455
Average rise time (hrs), D1_3-7 | 1.8039 |  |  |  |  | D1_5-7_Z | 3160.6033
Average rise time (hrs), D1_8-10 | 0.91951 |  |  |  |  | D1_8-10_Z | 944.3891
Average rise time (hrs), D1_11-12 | 0.78463 |  |  |  |  | D1_11-13_Z | 499.2673
Average rise time (hrs), D1_13-17 | 2.1196 |  |  |  |  | D1_14-16_Z | 4013
Average rise time (hrs), D1_18-19 | 2.0498 |  |  |  |  | D1_17-19_Z | 4674.47
Average rise time (hrs), D1_21-25 | 2.5593 |  |  |  |  | D1_21-25_Z | 5200
Rise time (hrs), D1_17 | 2.036 |  |  |  |  | D1_17_Z | 4628.69
Rise time (hrs), D1_16 | 2.3623 |  |  |  |  | D1_16_Z | 4668.2
Rise time (hrs), D1_15 | 2.2752 |  |  |  |  | D1_15_Z | 4433
Rise time (hrs), D1_14 | 1.7214 |  |  |  |  | D1_14_Z | 2937.8
Rise time (hrs), D1_13 | 1.0117 |  |  |  |  | D1_13_Z | 1248.49
Rise time (hrs), D1_12 | 0.68619 |  |  |  |  | D1_12_Z | 174.434
Rise time (hrs), D1_11 | 0.65602 |  |  |  |  | D1_11_Z | 74.8779
Average rise time (hrs), D2_1-3 | #REF! |  |  |  |  | D2_1-3_Z | #REF!
Average rise time (hrs), D2_4-5 | #REF! |  |  |  |  | D2_4-5_Z | #REF!
Average rise time (hrs), D2_6 | #REF! |  |  |  |  | D2_6_Z | #REF!
Average rise time (hrs), D2_7 | #REF! |  |  |  |  | D2_7_Z | #REF!
Average rise time (hrs), D2_8-10 | #REF! |  |  |  |  | D2_8-10_Z | #REF!
Average rise time (hrs), D2_11 | #REF! |  |  |  |  | D2_11_Z | #REF!
Average rise time (hrs), D2_11-12 | #REF! |  |  |  |  | D2_11-12_Z | #REF!
Average rise time (hrs), D1_S | 1.5724
Average rise time (hrs), D2_N | 1.2672
Average rise time (hrs), D2_S | 1.2672
Burn time (hrs) | 0.33333
rec_time (hrs) | 0.3
PSN Calculator |  | X | Vwat | Vman | Dt(min) |  | Dx (km)
(15s added to calc w/out DX) |  | 160 | 1.5 | 8 | 1.6944 |  | 0.23536
[5 empty] | Dt(sec) |  | Dx (m)
MCS shot spacing |  |  |  |  | 21.5983 |  | 50
|  | X | dx | nchan | T | dt | Gb
MCS Data recorded |  | 1900 | 0.05 | 480 | 15 | 0.002 | 547.2
PSN Calculator | X | XR | TR | Vwat | Vman | Uw | Um | Dt(min) | Dx (km)
(cross-over calculation with Dx + 15s) | 160 | 25 | 20 | 1.5 | 8 | 0.66667 | 0.125 | 1.4129 | 0.19625

## Insts_09_02_20
lon | lat | X | # | use | Line | depth
-172.464 | 52.4509 | 0 | 1 | 2 | S1 | -204.669
-172.682 | 52.4299 | 15 | 2 | 2 | S1 | -540.91
-172.9 | 52.4086 | 30 | 3 | 1 | S1 | -991.433
-173.117 | 52.3868 | 45 | 4 | 1 | S1 | -873.855
-173.3198 | 52.3661 | 59 | 5 | 1 | S1 | -672.0208
-173.4935 | 52.3481 | 71 | 6 | 1 | S1 | -615.5221
-173.667 | 52.3299 | 83 | 7 | 1 | S1 | -359.2231
-173.8404 | 52.3113 | 95 | 8 | 1 | S1 | -109.7305
-174.5678 | 52.2452 | 143 | 9 | 2 | S1 | -99.2563
-174.633 | 52.2233 | 150 | 10 | 2 | S1 | -106.426
-174.748 | 52.21 | 158 | 11 | 4 | S1 | -122.35
-174.9063 | 52.1916 | 169 | 12 | 1 | S1 | -140.895
-175.0642 | 52.173 | 180 | 13 | 1 | S1 | -281.69
-175.222 | 52.1541 | 191 | 14 | 1 | S1 | -211.256
-175.3797 | 52.1351 | 202 | 15 | 1 | S1 | -114.912
-175.58 | 52.1106 | 216 | 16 | 1 | S1 | -118.472
-175.709 | 52.0946 | 225 | 17 | 1 | S1 | -167.507
-175.828 | 52.0798 | 233.3 | 18 | 1 | S1 | -154.236
-176.316 | 52.0174 | 267.5 | 19 | 2 | S1 | -173.976
-176.451 | 51.9997 | 277 | 20 | 2 | S1 | -332.907
-176.8849 | 51.9418 | 307.5 | 21 | 2 | S1 | -409.3844
-176.977 | 51.9293 | 314 | 22 | 2 | S1 | -179.961
-177.275 | 51.8883 | 335 | 23 | 1 | S1 | -923.723
-177.3318 | 51.8803 | 339 | 24 | 1 | S1 | -1182.6139
-177.5102 | 51.8554 | 353 | 25 | 1 | S1 | -300.4861
-178.147 | 51.7635 | 396.7 | 26 | 1 | S1 | -237.914
-178.292 | 51.742 | 407 | 27 | 1 | S1 | -570.363
-178.489 | 51.7126 | 421 | 28 | 2 | S1 | -1072.47
-178.686 | 51.6828 | 435 | 29 | 2 | S1 | -727.119
-178.896 | 51.6505 | 450 | 30 | 2 | S1 | -687.512
-175.144 | 53.236 | 0 | 1 | 2 | D1 | -3758.55
-175.092 | 53.1048 | 15 | 2 | 2 | D1 | -3767.36 | D1_1-4_Z | 3673.455
-175.041 | 52.9737 | 30 | 3 | 2 | D1 | -3692.23 | D1_1-2_Z | 3762.955
-174.993 | 52.8512 | 44 | 4 | 2 | D1 | -3475.68 | D1_5-7_Z | 3160.6033
-174.946 | 52.7287 | 58 | 5 | 1 | D1 | -3426.68 | D1_8-10_Z | 944.3891
-174.905 | 52.6237 | 70 | 6 | 1 | D1 | -3221.33
-174.865 | 52.5187 | 82 | 7 | 1 | D1 | -2833.8
-174.825 | 52.4137 | 94 | 8 | 4 | D1 | -2238.97
-174.785 | 52.3086 | 106 | 9 | 4 | D1 | -496.18
-174.727 | 52.1601 | 123 | 10 | 0 | D1 | -98.0174
-174.648 | 51.95 | 147 | 11 | 2 | D1 | -74.8779
-174.609 | 51.8449 | 159 | 12 | 2 | D1 | -174.434
-174.569 | 51.7398 | 171 | 13 | 2 | D1 | -1248.49
-174.531 | 51.6347 | 183 | 14 | 1 | D1 | -2937.8
-174.485 | 51.5121 | 197 | 15 | 1 | D1 | -4433 | D1_11-13_Z | 499.2673
-174.441 | 51.3894 | 211 | 16 | 1 | D1 | -4668.2 | D1_14-16_Z | 4013
-174.396 | 51.2667 | 225 | 17 | 2 | D1 | -4628.69 | D1_17-19_Z | 4674.47
-174.348 | 51.1352 | 240 | 18 | 2 | D1 | -4589.99 | D1_21-25_Z | 6155.1733
-174.301 | 51.0037 | 255 | 19 | 2 | D1 | -4804.73
-174.254 | 50.8722 | 270 | 20 | 0 | D1 | -6156.13
-174.208 | 50.7406 | 285 | 21 | 3 | D1 | -7137.88
-174.161 | 50.6091 | 300 | 22 | 0 | D1 | -6974.5
-174.115 | 50.4775 | 315 | 23 | 3 | D1 | -6106.06
-174.069 | 50.3459 | 330 | 24 | 0 | D1 | -5525
-174.023 | 50.2142 | 345 | 25 | 1 | D1 | -5221.58
-173.978 | 50.0826 | 360 | 26 | 0 | D1 | -4967.99
-173.932 | 49.9509 | 375 | 27 | 0 | D1 | -4496.5
-173.887 | 49.8192 | 390 | 28 | 0 | D1 | -5183.05
-173.843 | 49.6875 | 405 | 29 | 0 | D1 | -5168.81
-173.798 | 49.5558 | 420 | 30 | 0 | D1 | -4921.28
-173.754 | 49.4241 | 435 | 31 | 0 | D1 | -4650.93
-173.71 | 49.2923 | 450 | 32 | 0 | D1 | -5532.8
-176.652 | 52.9124 | 0 | 1 | 0 | D2 | -3733.28 | D2_1-2_Z | 3742.9753
-176.5821 | 52.7285 | 21 | 2 | 0 | D2 | -3752.6706 | D2_3-5_Z | 3257.7071
-176.5124 | 52.5447 | 42 | 3 | 0 | D2 | -3567.312 | D2_6_Z | 163.947
-176.4466 | 52.3695 | 62 | 4 | 0 | D2 | -3327.9793 | D2_6-8_Z | 410.1713
-176.3813 | 52.1942 | 82 | 5 | 0 | D2 | -2877.8299
-176.281 | 51.9226 | 113 | 6 | 4 | D2 | -163.947
-176.207 | 51.7209 | 136 | 7 | 0 | D2 | -129.725
-176.1445 | 51.5455 | 156 | 8 | 0 | D2 | -936.8419
-176.0815 | 51.3701 | 176 | 9 | 0 | D2 | -3808.4903
-176.016 | 51.1859 | 197 | 10 | 0 | D2 | -4227.6419 | D2_9-10_Z | 4018.0661
-175.951 | 51.0016 | 218 | 11 | 0 | D2 | -3615.6969 | D2_11-14_Z | 5614.5283
-175.8835 | 50.8085 | 240 | 12 | 0 | D2 | -5218.4461 | D2_15-16_Z | 6655.195
-175.837 | 50.6769 | 255 | 19 | 0 | D2 | -6321.84
-175.792 | 50.5452 | 270 | 20 | 0 | D2 | -7302.13
-175.747 | 50.4135 | 285 | 21 | 0 | D2 | -7231.78
-175.702 | 50.2817 | 300 | 22 | 0 | D2 | -6078.61